## Actions
| Event Planning |  |  |  |  | Rev 2
| Name of Event: |  | Review Date: |  | 2025-04-15
| Event Owner: |  | Next Planned Review Date: |  | 2025-04-22
| Date of Event: | 2025-06-02 | Review Team: |  | Bryan, Joe, Connie, Taryn
Location of Event:
# | Item | Notes | Item Owner | Days Prior to Event | Planned Dates | Status
1 | Leadership Approval for event completed | This includes identification and approval of: • Process to be Leaned • Baseline goal and metrics • Key Objectives • Expected Financial Results |  | 30 | 2025-05-03
2 | Establish Attendee List - Within Business | A cross-functional team of attendees should include at least one Subject Matter Expert from each sub process (e.g. Sales, Marketing, Finance, Procurement, Manufacturing, Engineering, etc) as well as representation from the key enabling support functions (e.g. HR) |  | 21 | 2025-05-12
3 | Establish Attendee List -Outside Business | Attendee list should also include people from within the country/region who will benefit from exposure to the lean process in order to take back learnings to share within their own business |  | 30 | 2025-05-03
4 | Obtain agreement from Business Leader and Senior Management Team on Attendee List | Total should not exceed 20 people |  | 20 | 2025-05-13
5 | Reserve 1 large conference/training room for the event | The training room requires large wall space for process mapping (recommended 40 ft.). A best practice is to remove any conference tables or large furniture in order to free up floor space. The event must take place within the business facility versus off-site. |  | 15 | 2025-05-18
6 | Send invitation for Event to attendees | Send invitation for Event to attendees |  | 15 | 2025-05-18
7 | Gather detailed process maps, if they exist, and gain agreement from process owners. | Gather detailed process maps (Level 3), if they exist, and gain agreement from process owners. |  | 14 | 2025-05-19
8 | Gather existing data |  |  | 14 | 2025-05-19
9 | Schedule weekly - bi-weekly conference calls with facilitators to ensure all action items leading into Event are completed |  |  | 21 | 2025-05-12
10 | Arrange for two translators and translator equipment, if necessary |  |  | 30 | 2025-05-03
11 | Provide any local hotel and restaurant recommendations for any out of town participants. | Also include directions and maps from the airport to the hotel and from the hotel to the business |  | 30 | 2025-05-03
12 | Team leaders discuss event and expectations to Associates prior to event asking for cooperation and assistance during the Event |  |  | 14 | 2025-05-19
13 | Arrange for catering | Lunch should be provided each day. Coffee/tea/water, biscuits/cookies, snacks, fruit, and soft drinks should be available throughout the day for the participants. There may be a need to order in a meal in the event the teams need to work late into the evenings (very common on Thursday night) |  | 7 | 2025-05-26
14 | Distribute agenda and any additional information to Attendees prior to commencement of Event | It is a best practice to post the agenda on the wall of the training room at the event and check off items throughout the day as they are accomplished |  | 7 | 2025-05-26
16 | Prepare high level Business Overview for Event that will be delivered by the Business Leader during the kick-off. |  |  | 7 | 2025-05-26
17 | Send Senior Management Team meeting request invite to attend Lean Event Kick-off (first hour) |  |  | 7 | 2025-05-26
18 | Send Senior Management Team meeting request invite to attend report out of the Value Stream Maps and Events | Tuesday evenings for one week events or Friday late morning for two week events (1 hour for meeting) |  | 7 | 2025-05-26 |  | Monday at start of the event (8:00)
19 | Send SENIOR MANAGEMENT TEAM meeting request invite to attend Final Report-Out presentations at the end of the event | Friday late morning (1.5 hours for meeting) |  | 7 | 2025-05-26
20 | Arrange Flipcharts and extra flipchart paper for Training Room and each Breakout Room |  |  | 7 | 2025-05-26
21 | Arrange for security access passes for all off-site participants | If there is a guard or security desk, it is recommended to inform them of the event location in order to provide directions to out of town participants that first enter the facility |  | 7 | 2025-05-26
22 | Arrange for an LCD projector for the training room | Depending on the event, this may also be necessary for each breakout room |  | 7 | 2025-05-26
23 | Arrange supplies for the event |  |  | 7 | 2025-05-26
24 | Guest WiFi Access |  |  | 3 | 2025-05-30
25 | Create name tags for participants | Include function on the nametag |  | 3 | 2025-05-30
26 | Set up training room | • Determine desired set-up (small tables clustered, U-Shape, traditional, other) • Clean any white boards and other table surfaces • Set up and test any electronic equipment • Label the outside of the training room or door of training room with name of event (if necessary) • Ensure all training supplies that are needed for the event are in the room and queued for use. |  | 3 | 2025-05-30 |  | Prefer u-shape.
27 | Arrive early and be prepared | It is a best practice for the event facilitator to arrive and be available at least one hour in advance of the attendees on the first day of the event. For very early start times that may be established mid-week, plan to arrive at least 20 minutes ahead of the start time. |  | 0 | 2025-06-02
Formulas:
Bryan, Joe, Connie, Taryn = C5-[Days Prior to Event]

## Attendees
Andrea | Dir, Recovery Services |  | Dan | Sr Dir Ops Integration | Name | Function
Christie | Sr Mgr. Recovery Services |  | Shay | Supervisor WO
? |  |  | I'isha | Supervisor TP
|  |  | Grady | Supervisor TP wknd
|  |  | Varonica | Ops Support WO
|  |  | Terra | Ops Support WO
|  |  | ? | Processor WO
|  |  | ? | Lab Aide WO
|  |  | ? | Processor TP wknd
has working in both areas

## Attendees_
|  | Joe Rutz | Facilitator (Lean Horizons)
CORE TEAM | Technical design | Woody Wilson-Croome | Head of Technical
|  | Andrew Blacklock | Head of Technical
|  | James Spitzer | Technical Manager
|  | Lee Hayman | Technical Manager
| Commercial £ | Dave Saxby | Head of Commercial
| Delivery | Mike Rolfe | Construction Director
|  | Kieran Jones | Project Manager
| Planning | Brett Lambourne | Head of Planning
Sub / Support Team |  | James Begley | Bus. Ops & Tech Director
|  | Luke Taylor | Operations Director
|  | Sarah Rahn | Head of Development Marketing