## VAVE process map
Value Engineering / Value Analysis process map
Note:
Phase | Process | [9 empty] | Tools
Phase I: Concept
|  | Finance dept. | Understand product cost breakdown (COGS, mat, OH, labor, OSP, freight, Cost of Quality..) |  | VAVEng | Identify FGs covering majority of material used for product line |  |  |  |  | - | A3 Project Charter
- setup project charter | [10 empty] | - | Stakeholder analysis
- collect baseline information | [10 empty] | - | Voice of customer (product)
- draft project schedule | [10 empty] | - | Voice of customer (process)
[5 empty] | Sup.Chain | Obtain representative BOM |  |  |  |  | - | Finish good complexity analysis
[11 empty] | - | ABC costing
[11 empty] | - | Cost Analysis (Cost Cube)
-
[5 empty] | Sup.Chain | Prepare BOM Commodity cost breakdown
[5 empty] | PM | Sort items according to annual spend
[5 empty] | Team | Create Project Charter: - Objectives - Baseline - Team Roster - Scope (product range) - Timeline (Milestones) - Risks
[5 empty] | C. Team | Outline initial project schedule (or use template)
[5 empty] | PM | Prepare presentation for kick-off with CTMs
Phase II: Feasibility (Evaluation)
- Complete List of Proposals |  | C. Team | Brainstorm for cost reduction opportunities |  | CompEng | Identify EOL, Single S, Multi S, items with high cost |  |  | MFG Team | Evaluate Manufacturing quality, cost, leadtimes | - | Pareto
- Approval from customer to go ahead with changes | [10 empty] | - | Cost Analysis (Cost Cube)
[11 empty] | - | Brainstorming
- All samples ordered for Qualification | [10 empty] | - | Value Stream Mapping
|  | C. Team | Estimate savings for each opportunity |  | CompEng | Look up for alternative components |  |  |  |  | - | Component Value Analysis
- Qualification plan created | [10 empty] | - | Component comparison analysis
[11 empty] | - | Component complexity analysis
[11 empty] | - | Waste Analysis
|  | C. Team | Assign responsible for each brainstormed opportunity |  | Supply Ch. | Quote alternative components |  |  | MFG Team | Identify the non-value added activities | - | Takt Time
[11 empty] | - | Component Margin Analysis
[11 empty] | - | FG margin analysis
|  | C. Team | Get members to fill out activities/duration for each opportunity for traceability purposes |  | C. Team | Evaluate opportunities (Ele/Quality, Feasibility, Safety, Effort/Benefit) |  |  | MFG Team | Brainstorm for improvements & apply lean principles
[5 empty] | PM | Put toghether an initial List of Proposals |  |  | MFG Team | Evaluate MFG improvement (quality, delivery, cost) opportunities
[5 empty] | C. Team | Evaluate opportunities (Ele/Mech/PCB/Quality/Sourcing, Tooling, Safety, Effort/Benefit)
[9 empty] | MFG Team | Plan VSM future state (build MFG CR task list)
[5 empty] | C. Team | Prioritize & select opportunities, remove hi effort/low benefit items |  |  |  |  | - | Pugh Analysis
[11 empty] | - | Effort/Benefit prioritization
[5 empty] | PM | Update List of Proposals with new opportunities for CR
[5 empty] | PM | Update project schedule
|  | PM | Get customer approval for List of proposals | YES
NO
YES
NO
|  | C.Team | Revise the List of Proposals
[5 empty] | Supp.Chain | Order samples for qualification
[5 empty] | VAVEng | Create Qualification plan
[5 empty] | PM | Update Project Schdule (incl. sample LT)
Phase III: Design
[5 empty] | Core Team | Design (if applicable) |  |  | MFG Team | Implement changes in MFG according to plan | - | FMEA
[11 empty] | - | Risk Assessment
[11 empty] | - | Voice of customer
[5 empty] | Supp.Chain | Get test samples
Phase IV: Qualification
[5 empty] | VAVEng | Start Qualification
- all items qualified
No
Yes
|  | C. Team | Exclude component from implementation list
No
Yes
[5 empty] | Customer | Customer qualification
|  | C. Team | Investigate cause, take actions | No
Yes
Phase V: Ramp-Up (Implementation)
[5 empty] | VAVEng | ECO (PCN)
- standardized process - ECO closed and customer approval grated
[5 empty] | Team | Document, Communicate, Archive
[5 empty] | Supply Ch. | Monitor use up of items and date of start of savings
Key areas of analysis:
Quality, Lead time
BOM cost (design change/dual sourcing)
MFG cost
Component alternations
Freight cost
MFG Cost
Component PASS?
Custom product?
PASS?
End of process
Project Schedule
List of proposals
6-8 weeks
6-7 weeks
2 week
Deliverable
Activity list
Project Schedule
MFG CR tracker
1 week
0-5 weeks (runs along with qualification)
Qualification plan
Need customer approval?
Customer approved?
List of Proposals
BOM Evaluation
Component Alt.

## Sample Order (hidden)
DCA Value Engineering - Sample order decision process
|  |  |  | Supp.Chain | Get logistic details on samples (QTY, Cost, Lead times)
|  |  |  | C. Team | Set priority to qualifi- cation items based on $saving
|  |  |  | Supl.Ch | Get Purch dept to drive items for qualification based on Mat avail.
|  |  |  | C. Team | Finalize List of proposals
[6 empty] | C. Team | Risk Buy decision
| Proj.Mng | Create presentation (follow template) | Yes
| Proj.Mng | Involve Engineer, CQR & Marketing representative
No
| Proj.Mng | Organize conf call with customer, submit present. for approval
| Proj.Mng | Get customer approval to List of Proposals |  | Supp.Chain | Order Samples for qualification
Need cust.approval?